## Production
P-Code | Components | Sub Components | Production Plan Start | Production Actual Start | Production Forecast Start | Production Start Delay Reason | Production Plan Finish | Production Actual Finish | Production Forecast Finish | Prouduction Finsh Delay Reason | Serial Number | Final Qc

## Quality
P-Code | Components | Sub Components | Inspection Call Plan | Customer Inspection Actual | Customer Inprogress Inspection | MDCC Plan | MDCC Actual

## Dispatch
P-Code | Components | Sub Components | Dispatch Plan Start | Dispatch Actual Start | Dispatch Forecast Start | Dispatch Start Delay Reason | Dispatch Plan Finish | Dispatch Actual Finish | Dispatch Forecast Finish | Dispatch Finish Delay Reason | Frame No | Root Frame No | Tip Frame No | Transporter | Invoice Number | Invoice Date | vechile No | LR Number | LR Date | DC No | DC Date | Vechile in Date | Delivery Plan | Delivery Actual | Delivery Forecast | Delivery Delay Reason

## Receiving
P-Code | Components | Sub Components | Receiving Plan | Receiving Actual | MVC Date | Endorsed MVC | Deemed MVC | Issuance of Deemed MVC Date | Unload Delay Reason | Location Id | Maximo Id | Set Number | Serial Number | Component Condition | Return Status | Nacell Frame return Date | Hub Frame return Date | Blade Frame return Date | Gearbox Rotation Gear return Date

## Foundation
P-Code | WTG Qty | Location No. | Maximo ID | Soil Test Plan Start | Soil Test Actual Start | Soil Test Forecast Start | Soil Test Start Delay Reason | Soil Test Plan Finish | Soil Test Actual Finish | Soil Test Forecast finish | Soil Test Finish Delay Reason | Design SBC | Actual SBC (t/m2) | Excavation Plan Start | Excavation Actual Start | Excavation Forecast Start | Excavation Start Delay Reson | Excavation Plan Finish | Excavation Actual Finish | Excavation Forecast Finish | Excavation Finish Delay Reson | PCC Plan | PCC Actual | PCC Forecast | PCC Delay Reason | Bottom Flange Plan | Bottom Flange Actual | Bottom Flange Forecast | Bottom Flange Delay Reason | Top Flange Plan | Top Flange Actual | Top Flange Forecast | Top Flange Delay Reason | Renforcement Plan Start | Renforcement Actual Start | Renforcement Forecast Start | Renforcement Start Delay Reason | Renforcement Plan Finish | Renforcement Actual Finish | Renforcement Forecast Finish | Renforcement Finish Delay Reason | Earthing strip Plan | Earthing strip Actual | Earthing strip Forecast | Earthing Strip Delay Reason | Shuttering Plan | Shuttering Actual | Shuttering Forecast | Shuttering Delay Reason | Foundation Casting Raft Plan | Foundation Casting Raft Actual | Foundation Casting Raft Forecast | Foundation Casting Raft Delay Reason | Foundation Casting Pedestal Plan | Foundation Casting Pedestal Actual | Foundation Casting Pedestal Forecast | Foundation Casting Pedestal Delay Reason | Foundation 7 days cube test Date | Foundation 21 days cube test Date | Foundation 28 days cube test Date | Foundation Cube Test Delay Reason | Grouting Plan | Grouting Actual | Grouting Forecast | Grouting Delay Reason | Grouting 7 days cube test Date | Grouting 28 days cube test Date | Grouting Cube test Delay Reason | Backfilling Plan | Backfilling Actual | Backfilling Forecast | Backfilling Delay Reason | Approch Road Plan | Approch Road Actual | Approch Road Forecast | Approch Road Delay Reason | Crane Platform Plan | Crane Platform Actual | Crane Platform Forecast | Crane Platform Dely Reason | Loc Clear for Erection Plan | Loc Clear for Erection Actual | Loc Clear for Erection Forecast | Loc Clear for Erection Delay Reason
P-8001 | 15 |  |  | Step 1 | [9 empty] | Step 2 | [7 empty] | Step 3 |  |  |  | Step 4 | [7 empty] | Step 5 | [7 empty] | Step 6 |  |  |  | Step 7 |  |  |  | Step 8 |  |  |  | Step 9 |  |  |  | Step 10 |  |  |  | Step 11 |  |  |  | Step 12 |  |  | Step 13 |  |  |  | Step 14 |  |  |  | Step 15 |  |  |  | Step 16

## Installation
P-Code | WTG Qty | Location No. | WTG Type | TowerType | Maximo ID | Main Crane supplier | Main Crane model | Main Crane Mob | Start of main crane assembly | Finish of Main Crane Assembly | Bottom platform Assembly | Main Crane boom up | Converter Panel Installation | Installation Plan Start | Installation Actual Start | Installation Forecast Start | Installation Start Delay Reason | S1 tower section Installation | S2 tower section Installation | S3 tower section Installation | S4 tower section Installation | S5 tower section Installation | Nacelle Installation | Assembly Method | Rotor Assembly Date | Hub Assembly Date | Blade1 Installation | Blade2 Installation | Blade3 Installation | Max of three blade | Rotor Installation Date | Installation Plan Finish | Installation Actual Finish | Installation Forecast Finish | Installation Finish Delay Reason | Main crane boom Down | Anchor bolts 10% torque check | S1 Upper bolts 10% torque check | S2 Upper bolts 10% torque check | S3 Upper bolts 10% torque check | S4 Upper bolts 10% torque check | Tower-Nacelle bolts 10% torque check | Nacelle-Hub bolts 10% torque check | Blade1 bolts 10% torque check Date | Blade2 bolts 10% torque chec | Blade3 bolts 10% torque check | Rotor Bolts 10% torque check | 10% Final Torquing Completed | Generator Alignment Date | Cable Laying Date | machanical Completion | Electrical Completion | Lift Installation Date | QA Inspection Finish Date | MCC Plan | MCC Actual | MCC Forecast | MCC Delay Reason | MCC Sign Off Date
|  |  | EN 156 | 120HH-374TT

## Commissioning
Sr. | Cutomer | P-Code | Projects | State | SPV 1/2/3/ | Proj QTY | PRE-COMMISSIONING |  |  |  |  | COMMISSIONING | [11 empty] | STPT | [8 empty] | HOTO
1 |  | P-8001 | India_Renew1_Gadag_KA_300.3MW | KARNATAKA |  | 91 | PRE-COM | Bottom commissioning | Nacelle Comm | Hub Comm | Sign Off | Commissioning Plan | Commissioning Actual | Commissioning Forecast | Commissioning Delay Reason | USS Charge | WTG Charge | Converter Test | Generation Trial | Real Time Validation | MPPC / PPC | COD | Certificate Sign Off | STPT Plan Start | STPT Acual Start | STPT Forecast Start | STPT Start Delay Reason | STPT Plan Finish | STPT Actual Finish | STPT Forecast Finish | STPT Finish Delay Reason | STPT Sign Off | HOTO Plan Start | HOTO Actual Start | HOTO Forecast Start | HOTO Start Delay Reason | HOTO Plan Finish | HOTO Actual Finish | HOTO Forecast Finish | HOTO Finish Delay Reason | HOTO Sign Off